## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 Wokring App? | 8
Task Create DB |  | John Sh. | Compelete | 7 | 5 | 3 | 0 | 0 | 0 | 0
Task Test DB |  | ALL | Complete | 3 | 1 | 1 | 5 | 0 | 1 | 0
Task Creat Backend |  | Rami H. | In progress | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Task Test Backend |  | ALL | Not started | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
User Story #2 Search for doctor | 7
Task Create UI |  | Ali Z. | Not started | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task Connect to Backend |  | Nawar A. | Not started | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task Create Advanced UI |  | Nawar A. | Not started | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task Test |  | Ali Z. | Not started | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 Schedule | 5
Task Design UI |  | Ali Z. | Not started | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task Create UI |  | Nawar A. | Not started | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task Connect to Backend |  | Nawar A. | Not started | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task Test |  | ALL | Not started | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 Reserve | 8
Task Design UI |  | Ali Z. | Not started | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task Create UI |  | Nawar A. | Not started | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task Connect to Backend |  | Nawar A. | Not started | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task Test |  | ALL | Not started | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 Cancel Appointment | 3
Task Design UI |  | Ali Z. | Not started | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task Create UI |  | Nawar A. | Not started | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task Connect to Backend |  | Nawar A. | Not started | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task Test |  | ALL | Not started | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 18 | 14
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.